## concreat holdings — customer po
Concreat Holdings — Customer Portal (Concreat Hub)
Build tracker for the Concreat Hub customer portal (Business Central + Power Platform). For internal PASI staff and outsourced developers — task-level detail only, no commercial/costing figures.
Full Portal — Nov 15, 2026 (PROPOSED — pending dev capacity confirmation)
Name | Subitems | Status | Portal Section | Role | Assigned To | Timeline - Start | Timeline - End | Functional Detail | Depends On
Dashboard — Greeting & company context |  | Not Started | Dashboard | Power Platform Developer | Adrian Celis, reco@automations365.com, Michael Peralta Tabilin | 2026-09-25 | 2026-11-13 | Time-of-day greeting with the customer's name; company name shown in the greeting subtext and kept in sync when the customer switches companies.
Navigation — Concreat logo on every page |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, reco@automations365.com, Michael Peralta Tabilin | 2026-09-25 | 2026-11-13 | The Concreat Holdings logo mark appears in the shared topbar on every page, not just sign-in.
Navigation — Folder order & rename |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, reco@automations365.com, Michael Peralta Tabilin | 2026-09-25 | 2026-11-13 | Nav reordered to Dashboard, Delivery Sites, Orders, Customer Ledger, Document Center, Requests, Complaints & Feedback, Account and User Management; "Account" renamed to "Account and User Management."
New Order — Single Order entry |  | Not Started | Orders | Power Platform Developer | Adrian Celis, reco@automations365.com, Michael Peralta Tabilin | 2026-09-25 | 2026-11-13 | Order lines pull item, quantity/UOM, and pricing directly from Business Central — nothing recalculated on the portal. Covers the Single Order flow end-to-end, item selection through review.
Orders List — filters, search, status, pagination |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-25 | 2026-11-13 | Search by SO number/PO reference; filter by status, delivery site, and date range; paginated results table with status pills matching BC's Sales Order statuses.
Trip ID display (pending/ready states) |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-25 | 2026-11-13 | Shows pending/ready state for the delivery trip ID on each order once assigned.
New Order — Delivery & Fulfillment card (Source field) |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-25 | 2026-11-13 | Shipment method (Pickup/Delivery), Source dropdown (plain customer-facing label only, no BC/location-code terminology), delivery site, receiving details, and dates. Shared across Single and Blanket order types.
Delivery Sites — Registered sites list |  | Not Started | Delivery Sites | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-25 | 2026-11-13 | Table of the customer's registered delivery locations (code, name, address), sourced from Business Central Ship-to records.
BC Extension — Available Credit real-time check |  | Not Started | BC Extension | BC Integration Specialist | Mark Joseph Anonuevo, Aira Samson | 2026-09-25 | 2026-11-13 | Business Central-side extension exposing real-time available credit to the portal — feeds the credit-standing check on New Order and the Dashboard's Available Credit tile.
New Order — Freight & Other Charges |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-25 | 2026-11-13 | Freight and other line-item charges shown alongside order lines in the order summary.
BC Extension — Freight & Other Charges integration |  | Not Started | BC Extension | BC Integration Specialist | Mark Joseph Anonuevo, Aira Samson | 2026-09-25 | 2026-11-13 | Business Central-side extension to sync freight/other charges entered on New Order back into the Sales Order in BC.
BC Extension — Receiving-details integration |  | Not Started | BC Extension | BC Integration Specialist | Mark Joseph Anonuevo, Aira Samson | 2026-09-25 | 2026-11-13 | Business Central-side extension to capture/sync delivery receiving details (contact, instructions) entered on New Order.
Orders — Upload Orders (Excel) |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-11-26 | 2026-12-01 | New button opens a modal to attach a plain Excel file (no fixed template) plus an optional note. Submission routes to PASI's service center for manual encoding into Business Central — no parsing, validation, or auto-sync in this release.
Orders List — full-width caption layout fix |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-12-02 | 2026-12-02 | Layout fix: the descriptive caption under the Orders heading now spans the full row instead of being squeezed by the action buttons.
Dashboard — Account Overview stat tiles |  | Not Started | Dashboard | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-11-27 | 2026-11-30 | Balance, Balance due, Overdue amount, Credit limit, and Available credit tiles, sourced from Business Central. Descriptive text under the heading removed per the September 19 change (item 9) — tiles themselves stay.
Navigation — Text, wordings & naming conventions |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com |  |  | Item 15, confirmed Sept 22, 2026, folded in at no additional cost. Renames: "Upload Orders (Excel)" → "+ New Multiple Order" on Orders; "Requestor" → "Submitted By" on the Complaints tab specifically (Commendation and Requests keep existing labels); Dashboard's Balance / Balance due tiles → Outstanding Balance / Balance Due Today.
Navigation — Consistent export button placement & labeling |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com |  |  | Item 18, confirmed Sept 22, 2026. Export control placed last in the toolbar in every module that has one (Orders, Customer Ledger, Document Center), each standardized to a single ⬇ Download CSV/Excel label and icon. Cuts across three modules — sequence after each module's own build.
Drafts tab |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | In-progress orders saved but not yet submitted.
Pending Approval tab |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Orders awaiting credit approval, with an auto-approved confirmation message once cleared.
Orders List — Export to Excel |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Exports every order matching the active filters (not just the visible page) as an .xlsx file.
New Order — Credit standing check before submit |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Validates the order against the customer's available credit (see the Available Credit BC Extension task) before allowing submission; surfaces a clear message if the order would exceed the limit. | BC Extension — Available Credit real-time check
Blanket Orders tab |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Lists confirmed Blanket Sales Orders; each drawdown Sales Order shows its Blanket SO # and links back here.
New Order — Blanket Order entry |  | Not Started | Orders | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Draws down against an existing Blanket Sales Order; the resulting Sales Order references the Blanket SO # and appears on both the Orders and Blanket Orders tabs.
Customer Ledger — Statement table |  | Not Started | Customer Ledger | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Statement of account — invoices, payments, credit memos, and running balance — sourced from Business Central.
Navigation — Active folder highlighting |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | The active nav item shows bold and underlined with an accent glow bar, so customers can see where they are in the portal.
Dashboard — Sales statistics tiles |  | Not Started | Dashboard | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Five clickable status tiles (Open, Pending Prepayment, Ready for Dispatch, Completely Shipped, Invoiced) showing live counts; clicking one jumps to the Orders list pre-filtered to that status.
Customer Ledger — Balance/credit tie-out to Dashboard |  | Not Started | Customer Ledger | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Ensures Customer Ledger and the Dashboard's Account Overview tiles read from the same Business Central source, so figures never drift apart between the two screens.
Delivery Sites — Request a change |  | Not Started | Delivery Sites | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Request an update to an existing site's contact or address details; routed for internal review rather than a direct self-service edit.
Delivery Sites — Request removal |  | Not Started | Delivery Sites | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Mark a registered site for removal; routed for internal review.
Account and User Management — Contacts & portal access list |  | Not Started | Account and User Management | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Lists who on the customer's team has portal access and their role/permissions.
Account and User Management — Company information panel |  | Not Started | Account and User Management | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Read-only customer number, address, company name, VAT registration number, and website, sourced from the Business Central customer record.
Customer Ledger — Filters & search |  | Not Started | Customer Ledger | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Filter by date range and transaction type; search by reference number.
Dashboard — Announcement banner |  | Not Started | Dashboard | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Single admin-set announcement banner (title + message), set directly by the account team — no images or scheduling in this release.
Delivery Sites — Request a new site |  | Not Started | Delivery Sites | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Request a delivery location not yet on the account, with contact details; routed for internal review.
Navigation — In-portal help |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Nov 15 scope: basic only, per Concreat Holdings' Sept 27, 2026 request — the one-paragraph overview per section (8 short blurbs, one per module), reachable from a help link on every page. The 6 numbered step-by-step task guides for common workflows move to Phase 2, along with keeping those guides in sync as Requests/Complaints & Feedback reach full scope there.
Navigation — Full-width descriptive text (5 modules) |  | Not Started | Navigation / Global | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Confirmed Sept 23, 2026, no additional cost. Descriptive text under the section heading now spans the full page width instead of the first column only — applied to Delivery Sites, Customer Ledger, Document Center, Requests, and Account and User Management (Orders already has this as its own item).
Document Center — Document library & type filter |  | Not Started | Document Center | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Build the document library list with a document-type filter (Invoice, Delivery Receipt, Acknowledgement Receipt, and other order-related document types). Sales Order Confirmation is excluded from this list per the September 19 change review.
Requests — List & filters |  | Not Started | Requests | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Build the Requests list view with search plus filters for category, assigned group, and status.
Requests — Category / Request Type / Assigned Group cascade |  | Not Started | Requests | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Nov 15 scope trimmed per Concreat Holdings' Sept 27, 2026 request: 6 of 11 categories ship for Nov 15 — Sales Order, Trip Reference, Delivery, Document Copy, CHP Ordering Tool, and Other Request (all routed to Service Center or Logistics, the teams already engaged for the Orders/Delivery beta). The remaining 5 — Adjustment, Customer Account, Sample Request, Account Receivables, Technical Client Visit (routed to Finance, Credit, or Technical Services) — move to Phase 2. Build the Requests category cascade, each driving its own request type, assigned group, and category-specific extra fields.
Document Center — Search |  | Not Started | Document Center | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Add search within the Document Center by Sales Order number, PO reference, and document number.
Complaints & Feedback — Preferred contact method & contact person |  | Not Started | Complaints & Feedback | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Nov 15 scope narrowed to the Complaints tab only, per Concreat Holdings' Sept 27, 2026 request to trim this module — applies to Survey and Commendation once those ship in Phase 2. Add preferred contact method and contact person capture to the Complaints tab.
Complaints & Feedback — Category/type dropdown adjustments |  | Not Started | Complaints & Feedback | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Item 8 (Complaints half), confirmed Sept 23, 2026. Applies within the Complaints tab, which is the only Complaints & Feedback tab shipping Nov 15. Delivery & Handling category reassigns the Dispatch Coordination Issue complaint type from Assigned Group Operations to Logistics. All other category/type/assigned-group mappings unchanged.
Document Center — Cross-reference consistency |  | Not Started | Document Center | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Verify documents shown here tie back to the same order and delivery-site references shown in Orders and Customer Ledger, so a customer can cross-check the same order across sections.
Requests — Submission form |  | Not Started | Requests | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Build the Requests submission form: base fields, preferred-contact-method toggle, plus the category-specific fields driven by the cascade.
Complaints & Feedback — Complaints tab |  | Not Started | Complaints & Feedback | Power Platform Developer | Adrian Celis, Michael Peralta Tabilin, reco@automations365.com | 2026-09-29 | 2026-11-13 | Nov 15 scope: this is the only Complaints & Feedback tab shipping for Nov 15 (Survey and Commendation tabs move to Phase 2, per Concreat Holdings' Sept 27, 2026 request to trim this module). Build the Complaints tab on the original Release 1 cascade: category selection identifies the complaint type and assigned group. Includes incident date, delivery site, attachment upload, and consent capture.
[6 empty] | 2026-09-25 | 2026-12-02